## Computation Sheet NEW
EDIT ONLY BLUE TEXT |  |  |  |  | U.S. Department of Transportation
Federal Highway Administration
ENGINEER'S ESTIMATE ESCALATION COMPUTATION
PROJECT NO. AND NAME |  |  |  | Annual Escalation Rate
CA PFH 65-3(6) Beech Grove to Indian Creek |  |  |  | 4%
PROJECT MANAGER |  |  | ATTACH ORIGINAL ESTIMATE (Use separate sheet for each schedule and option)
Jane Doe |  |  | Schedule A
| PROGRAM AMOUNT DATE |  | PROGRAM AMOUNT
| 2025-09-15 |  | 12000000
| ENGINEER'S ESTIMATE DATE |  | ENGINEER'S ESTIMATE
| 2024-10-01 |  | 10500000
| ESCALATED ENGINEER'S ESTIMATE DATE |  | ESCALATED ENGINEER'S ESTIMATE
| 2025-09-15 |  | 12415000
CALCULATIONS
Begin Date 1 | End Date 1 | Escalation rate per year | # Months projecting 2 | Escalation (approx., rounded up to nearest $5,000) | Escalated Engineer's Estimate (does not include CE)
2024-10-01 | 2024-12-31 | 4% | 3 | 105000 | 10605000
2025-01-01 | 2025-12-31 | 4% | 12 | 425000 | 11030000
2026-01-01 | 2026-12-31 | 4% | 12 | 445000 | 11475000
2027-01-01 | 2027-12-31 | 4% | 12 | 460000 | 11935000
2028-01-01 | 2028-12-31 | 4% | 12.03 | 480000 | 12415000
|  |  | 0 | 0 | 0
Total Escalation |  |  |  | 1915000
NOTE | Typical long-term Construction inflation rates vary from 3-4% per year.
Verify escalation rate with the PM and Programmer.
INSTRUCTIONS
1). | Begin and End dates must be within the escalation rate dates for each period.
Verify the End date with the PM. The End date is typically the advertisement date.
2). | Months between the Begin and End dates are calculated by the application.
Form revised 04/22/2024