## READ FIRST
Instructions for Cost Estimate
1) | Choose a sample estimate that fits closest to your scope.
2) | Update the following:
| Assumed Construction Year: | 2029
*Current Call for Projects is projected to be programmed for FY28-29; choose last year to be conservative
3) | Update the yellow highlighted cells on the Estimate tab only for the following information: (Cost field will automatically adjust by formula.)
| a) Project Name |  | Delivery Year
| b) Scope of Work |  | 2022
| c) Work Items |  | 2023
| d) Unit Price |  | 2024
| e) Quantity |  | 2025
4) | Double check rounding in Total Project Cost (Rounded). |  | 2026
5) | Submit spreadsheet with application. |  | 2027
2028
| For additional information on estimating construction costs, please refer to: |  | 2029
| https://highways.dot.gov/federal-lands/estimates/cfl |  | 2030
2031
| Specifically, please refer to the CFL Engineer's Estimate Manual located here: |  | 2032
| https://highways.dot.gov/federal-lands/estimates/cfl/estimate-manual |  | 2033
2034
2035

## Sample 1 - Major Reconstruction
New Mexico FLAP Application Proposed Project Cost Estimate Sample 1
Sample Project # 1
1.1 miles of major reconstruction of an existing road, widening, improving roadway geometry, constructing rockfall catchment areas, new guardrail, slope armoring, drainage improvements, retaining walls and minor bridge rehabiliation - CFLHD delivered.
Work Item Description | Unit | Unit Price | Quantity | Cost | Remarks
Watering for Dust Control | LPSM | 30000 | 1 | 30000
Removals of Structures and Obstructions | LPSM | 20000 | 1 | 20000
Roadway Excavation | CUYD | 45 | 20000 | 900000
Waste | CUYD | 30 | 5000 | 150000
Aggregate Base | CUYD | 60 | 8000 | 480000 | Assume 6" Depth
Pavement Recycling | MILE | 120000 | 1.1 | 132000
Soil Nail/Rock Bolt/Mesh for slope armoring | LPSM | 150000 | 1 | 150000
Asphalt Pavement | TON | 180 | 4000 | 720000 | Assume 3" Depth
Bridge Repair, Railing | LPSM | 200000 | 1 | 200000
Retaining Walls | SQFT | 100 | 1000 | 100000 | Assume 10 ft tall x 400 ft
Drainage Improvements | LPSM | 300000 | 1 | 300000 | Assume 2500 ft of CMP, 70 ft of RCBC
Guardrail | LNFT | 35 | 1000 | 35000
Turf Re-establishment | ACRE | 3000 | 20 | 60000
Permanent Traffic Control & Striping | LPSM | 60000 | 1 | 60000
Right of Way Acqusition | LPSM | 40000 | 1 | 40000 | Assume 2 private parcels at approx. $20k each.
Utility Relocation | LPSM | 15000 | 1 | 15000 | Relocation of telephone line.
Subtotal |  |  |  | 3392000
% of above Subtotal
Mobilization | LPSM | 10% |  | 340000
Construction Survey and Staking | LPSM | 2% |  | 68000
Contractor Quality Control & Testing | LPSM | 5% |  | 170000
Temporary Erosion Control | LPSM | 3% |  | 102000
Clearing and Grubbing | LPSM | 2% |  | 68000
Temporary Traffic Control | LPSM | 8% |  | 272000
Subtotal |  |  |  | 4412000
Contingency (Required for all projects) | 30% | 1324000 |  |  | Refer to Table 1 in the CFL Engineer's Estimate Manual for guidance on contingencies
Inflation (Assumed 5% per year) | 5% | 904137
Total Construction (CN) | 2029 | 6640137
Preliminary Engineering (PE) (Required for all projects) | 12% | 796816.44
Construction Engineering (CE) (Required for all projects) | 12% | 796816.44
Total Project Cost | 8233769.88
Total Project Cost (Rounded) | 8240000
Formulas:
Unit Price = (F34+[Unit Price, row above])*((1+[Unit])^('READ FIRST'!$C5-YEAR(TODAY()))-1)

## Sample 2 - Rehabilitation
New Mexico FLAP Application Proposed Project Cost Estimate Sample 2
Sample Project # 2
10 miles of roadway rehabilitation including full depth reclamation, full depth asphalt, signing and striping - CFLHD delivered.
Work Item Description | Unit | Unit Price | Quantity | Cost | Remarks
Roadway Excavation | CUYD | 40 | 5000 | 200000
Roadway Aggregate (for shouldering) | CUYD | 50 | 8000 | 400000 | Assume 10 miles x 4 ft x 6" depth
Full Depth Reclamation | SQYD | 8 | 141000 | 1128000
Asphalt Pavement | TON | 160 | 27000 | 4320000 | Assume 10 miles x 28 ft x 3"
Drainage Improvements | LPSM | 200000 | 1 | 200000
Guardrail | LNFT | 35 | 4000 | 140000
Permanent Erosion Control | LPSM | 50000 | 1 | 50000
Permanent Traffic Control & Striping | LPSM | 75000 | 1 | 75000
Subtotal |  |  |  | 6513000
% of above Subtotal
Mobilization | LPSM | 10% |  | 652000
Construction Survey and Staking | LPSM | 2% |  | 131000
Contractor Quality Control & Testing | LPSM | 5% |  | 326000
Temporary Erosion Control | LPSM | 5% |  | 326000
Clearing and Grubbing | LPSM | 5% |  | 326000
Temporary Traffic Control | LPSM | 8% |  | 522000
Subtotal |  |  |  | 8796000
Contingency (Required for all projects) | 30% | 2639000 |  |  | Refer to Table 1 in the CFL Engineer's Estimate Manual for guidance on contingencies
Inflation (Assumed 5% per year) | 5% | 1802441.875
Total Construction (CN) | 2029 | 13237441.875
Preliminary Engineering (PE) (Required for all projects) | 12% | 1588493.025
Construction Engineering (CE) (Required for all projects) | 12% | 1588493.025
Total Project Cost | 16414427.925
Total Project Cost (Rounded) | 16420000
Formulas:
Unit Price = (F26+[Unit Price, row above])*((1+[Unit])^('READ FIRST'!$C5-YEAR(TODAY()))-1)

## Sample 3 - Parking Lot
New Mexico FLAP Application Proposed Project Cost Estimate Sample 3
Sample Project # 3
Parking lot at a visitor's center with a short (0.2 mile) access road - CFLHD delivered.
Work Item Description | Unit | Unit Price | Quantity | Cost | Remarks
Removals of Structures and Obstructions | LPSM | 20000 | 1 | 20000
Embankment Construction | CUYD | 50 | 4500 | 225000
Roadway Aggregate | CUYD | 60 | 2200 | 132000 | Assume 8" depth x 47,000 sq. ft. area
Asphalt Pavement | TON | 180 | 1130 | 203400 | Assume 4" depth x 47,000 sq. ft. area
Concrete Curb and Gutter | LNFT | 40 | 1600 | 64000
Inlets | EACH | 4000 | 4 | 16000
Culvert Pipe | LNFT | 200 | 500 | 100000
Permanent Erosion Control (e.g., Topsoil, Seed and Mulch) | LPSM | 100000 | 1 | 100000 | Includes landscaping
Site Furnishings | LPSM | 25000 | 1 | 25000 | 3 picnic tables and 2 benches
Accessibility Ramps | EACH | 2000 | 4 | 8000
Sidewalk | SQYD | 120 | 600 | 72000 | Assume 5 ft wide x 120 ft long
Permanent Traffic Control | LPSM | 20000 | 1 | 20000
Utility relocations | LPSM | 40000 | 1 | 40000
Subtotal |  |  |  | 1025400
% of above Subtotal
Mobilization | LPSM | 12% |  | 124000
Construction Survey and Staking | LPSM | 2% |  | 21000
Contractor Quality Control & Testing | LPSM | 5% |  | 52000
Temporary Erosion Control | LPSM | 5% |  | 52000
Clearing and Grubbing | LPSM | 5% |  | 52000
Temporary Traffic Control | LPSM | 8% |  | 83000
Subtotal |  |  |  | 1409400
Contingency (Required for all projects) | 30% | 423000 |  |  | Refer to Table 1 in the CFL Engineer's Estimate Manual for guidance on contingencies
Inflation (Assumed 5% per year) | 5% | 288832.05
Total Construction (CN) | 2029 | 2121232.05
Preliminary Engineering (PE) (Required for all projects) | 15% | 318184.8075
Construction Engineering (CE) (Required for all projects) | 12% | 254547.846
Total Project Cost | 2693964.7035
Total Project Cost (Rounded) | 2700000
Formulas:
Unit Price = (F31+[Unit Price, row above])*((1+[Unit])^('READ FIRST'!$C5-YEAR(TODAY()))-1)

## Sample 4 - Share Use Path
New Mexico FLAP Application Proposed Project Cost Estimate Sample 4
Sample Project # 4
3 miles of paved shared use path with an anticipated boardwalk to avoid wetland impacts - CFLHD delivered.
Work Item Description | Unit | Unit Price | Quantity | Cost | Remarks
Removals of Structures and Obstructions | LPSM | 2000 | 1 | 2000 | 3 mile x 30 ft
Roadway Excavation | CUYD | 40 | 12000 | 480000 | 3 mile x 1 ft x 20 ft
Aggregate Base Material | TON | 60 | 8900 | 534000 | Assume 3 mile x 16 ft x 6"
Asphalt Pavement | TON | 160 | 2300 | 368000 | Assume 3 mile x 12 ft x 2"
Boardwalk | LNFT | 1300 | 1200 | 1560000 | Assume 1200 ft
Drainage Improvements | LPSM | 80000 | 1 | 80000 | Assume 240 lnft of CMP, end sections, and riprap
Permanent Erosion Control | LPSM | 40000 | 1 | 40000
Permanent Traffic Control & Striping | LPSM | 10000 | 1 | 10000
Utility Relocation | LPSM | 30000 | 1 | 30000 | 2 power poles will need to be relocated
Subtotal |  |  |  | 3104000
% of above Subtotal
Mobilization | LPSM | 12% |  | 373000
Construction Survey and Staking | LPSM | 2% |  | 63000
Contractor Quality Control & Testing | LPSM | 5% |  | 156000
Temporary Erosion Control | LPSM | 5% |  | 156000
Clearing and Grubbing | LPSM | 5% |  | 156000
Temporary Traffic Control | LPSM | 4% |  | 125000 | Lower % due to TTC needed at construction access points.
Subtotal |  |  |  | 4133000
Contingency (Required for all projects) | 35% | 1447000 |  |  | Increase contingency due to potential wetland impacts
Inflation (Assumed 5% per year) | 5% | 879547.5
Total Construction (CN) | 2029 | 6459547.5
Preliminary Engineering (PE) (Required for all projects) | 12% | 775145.7
Construction Engineering (CE) (Required for all projects) | 10% | 645954.75
Cost Estimate for Proposed Project | 7880647.95
Total Project Cost (Rounded) | 7890000
Formulas:
Unit Price = (F27+[Unit Price, row above])*((1+[Unit])^('READ FIRST'!$C5-YEAR(TODAY()))-1)

## Sample 5 - Intersection
New Mexico FLAP Application Proposed Project Cost Estimate Sample 5
Sample Project # 5
Intersection improvements to a National Wildlife Refuge on a high-speed divided highway - Local Public Agency delivered
Work Item Description | Unit | Unit Price | Quantity | Cost | Remarks
Removals of Structures and Obstructions | LPSM | 50000 | 1 | 50000
Roadway Excavation | CUYD | 50 | 2000 | 100000
Aggregate Base Material | TON | 60 | 2800 | 168000 | Assume two 0.25 mile x 20 ft x 9" depth
Asphalt Pavement | TON | 170 | 2000 | 340000 | Assume two 0.25 mile x 16 ft x 6" turn lanes
Drainage Improvements | LPSM | 80000 | 1 | 80000 | Assume 240 lnft of CMP, end sections, and riprap
Permanent Erosion Control | LPSM | 40000 | 1 | 40000
Permanent Traffic Control & Striping | LPSM | 25000 | 1 | 25000
Utility Relocation | LPSM | 200000 | 1 | 200000 | 5 power poles and buried fiber optic will need to be relocated
Subtotal |  |  |  | 1003000
% of above Subtotal
Mobilization | LPSM | 12% |  | 121000
Construction Survey and Staking | LPSM | 2% |  | 21000
Contractor Quality Control & Testing | LPSM | 5% |  | 51000
Temporary Erosion Control | LPSM | 5% |  | 51000
Clearing and Grubbing | LPSM | 5% |  | 51000
Temporary Traffic Control | LPSM | 15% |  | 151000 | Increased due to location
Subtotal |  |  |  | 1449000
Contingency (Required for all projects) | 35% | 508000 |  |  | Increase contingency due to potential wetland impacts
Inflation (Assumed 5% per year) | 5% | 308472.125
Total Construction (CN) | 2029 | 2265472.125
Preliminary Engineering (PE) | 12% | 271856.655 |  |  | Assumed direct costs only
Construction Engineering (CE) | 12% | 271856.655
Cost Estimate for Proposed Project | 2809185.435
Total Project Cost (Rounded) | 2810000 |  |  |  | The FLAP contribution will generally be a firm-fixed dollar amount when CFLHD isn't Lead Agency. Applicant responsible for 100% of cost overruns.
Formulas:
Unit Price = (F26+[Unit Price, row above])*((1+[Unit])^('READ FIRST'!$C5-YEAR(TODAY()))-1)