04/01/2024

Include if using a Section 304 pay item.

## Section 304. — FULL DEPTH RECLAMATION

**Construction Requirements**

**304.03 General.** Add the following:

Before starting full depth reclamation work, obtain approval of the Job-Mix Formula for pavement design and proposed construction schedule.

Complete pulverizing or processing and paving operations such that no portion of a pulverized or processed surface is left unpaved for more than 14 days.

Include if removal of the pavement section is necessary to correct the subgrade issues, such as making superelevation corrections or minor horizontal and vertical adjustments. This should only be used for specific areas and not for the entire project length.

Submit a plan for approval 14 days before beginning pulverizing. Include in the plan details on the following for the pulverized material and new aggregate (if required):

**(a) Processing**. Describe procedures, methods, equipment, and extents of processing.

**(b) Removal and handling.** Describe procedures, methods, sequencing, and equipment used for removing the pulverized material.

**(c) Storage.** If the pulverized material will be moved to a separate location and stored, provide relevant details for storing the material, such as duration and location of stockpiling the material. If applicable, stockpile material according to Subsections 314.04 and 314.05.

**(d) Quantities.** Show the anticipated quantities in cubic yards of pulverized material that will be processed, removed, stored (if applicable), and re-used.

**(e) Sequencing.** Describe the timing and order of operations to complete the work.

**(f) Mixing and placement locations.** Describe the locations where the pulverized material will be placed and mixed with new aggregate (if required).

**304.05 Pulverizing.** Add the following:

Remove the pulverized material for use as crushed aggregate at the locations shown in the plans.

**304.05A Preparing Surface.** (Added Subsection).

Prepare the surface on which the pulverized material is placed according to Section 204 or 303 as applicable.