INCLUDE SECTION 153 ON ALL PROJECTS.

$$153.00A

Section 153. — CONTRACTOR QUALITY CONTROL

Revised 09 April 2026

INCLUDE CLAUSES ##153.01A, ##153.08A, AND ##153.08B ON ALL PROJECTS

##153.01A

153.01.  Add the following:

This work also includes using Masterworks to prepare electronic CDRs and measurement notes (item postings and supporting field measurement documentation), including entering labor, equipment, subcontractors, and inspection records into the system.

##153.08A

153.08.  Delete the first sentence and substitute the following:

Maintain complete testing and inspection records by pay item and make them accessible to the CO.

$$153.08B

153.08(a).  Delete the Subsection and substitute the following:

(a) QC and construction operations reports. For each day of the contract, prepare a CDR using Masterworks. Enter initial data for Labor/Equipment and Subcontractors before beginning any work. Maintain and update the Labor/Equipment and Subcontractors data to reflect ongoing changes as they occur. Report operations or items of work separately, including the manpower and equipment assigned to each. Document inspection results, including observed deficiencies and corrective actions taken. Complete a CDR for each contractor and subcontractor working that day.

When submitting test results on material being incorporated into the work, report test results within the reporting times indicated in the sampling and testing requirements at the end of each Section.

Enter the following data into Masterworks:

(1) Subcontractor data.

(2) Labor/Equipment.

(a) All manpower and equipment, including contractor and subcontractors. Complete all data fields.

(b) Labor: Type/classification, move-in date, move-out date, hourly rate, the contractor or subcontractor, and name.

(c) Equipment: Type/classification, move-in date, move-out date, make, model, and year of equipment manufacture.

Ensure the QCM checks the box with the following statement to certify all CDRs:

“I certify that the information contained in this record is accurate and that work documented herein complies with the contract. Exceptions to this certification are documented as a part of this record.”

Submit the record and certification within 24 hours of performing the work. If the CDR is incomplete, contains errors, or is otherwise misleading, it will be rejected and returned in Masterworks with corrections noted. Correct and resubmit rejected CDRs within 24 hours. If chronic errors or omissions occur, correct the procedures used to produce the records.