## Risk Management Register
Status |  | Risk Type | Response Strategy |  | Construction | Cost |  | Exploit
Active |  | Threat | Avoid |  | Design | Time |  | Share
Dormant |  | Opportunity | Transfer |  | Environment | Scope |  | Enhance
Retired |  |  | Mitigate |  | External | Quality |  | Accept
|  |  | Accept |  | Organization
Project Management
Right of Way
Sample Risk Management Register for Project XXXX
Risk Identification | [7 empty] | Qualitative Risk Assessment | [9 empty] | Risk Response Plan |  | Monitoring and Control |  |  | Risk Allocation
# | RMP No. | Status | Functional Area | Risk Category | Cause | Effect | Threat or Opportunity | Primary Objective | Probability | Impact | Risk Matrix | [6 empty] | Response Strategy | Response Actions | Responsibile Entity | Interval or Milestone Check | Status: Date and Review Comments | Owner | Contractor
1 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
2 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
3 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
4 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
5 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
6 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
7 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
8 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
9 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
10 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
11 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
12 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
13 | [10 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
14 | [10 empty] | Probability | VH
H
M
[12 empty] | L |  | X
VL
[13 empty] | VL | L | M | H | VH
Impact
15 | [10 empty] | Probability | VH
H
M
[12 empty] | L |  | X
VL
[13 empty] | VL | L | M | H | VH
Impact
[11 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
[11 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
[11 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
Note on J11: See Risk Ranking
Note on K11: See Risk Ranking
Note on T11: For examples see: www.cflhd.gov/Project_Management/Documents/PPIGuidelines/TEMPLATES/Risk_Assessment_Questionnaire_template.doc
Note on U11: Enter Entity: EFL, VDOT, Design-Builder, etc.

## Risks by Functional Area
Risks Identified by Functional Area
When identifying risk it is important to specify the risk correctly. As a guideline for identifying risk, use the following risk statement structure to help fill in the appropriate columns on the risk register: "Because of the cause or condition that is true, a risk may occur, having an effect on either a cost, quality, scope or time objective." The list below provides a sampling of potential risks for various functional areas. Every project has unique risks that need to be tailored, adjusted from prior projects, or extended to new situations.
Design/Construction Project Sample Risk List | Generic Project Sample Risk List
Construction Risks | Technical, Quality, or Performance Risks
Unidentified utility impacts | Examples include reliance on unproven or complex technolgy, unrealistic performance goals, long term performance, process roadblocks, new emerging initiatives, increases in complexity, etc..
Unexpected archeological findings
Changes during construction not covered by the contract
Unidentified hazardous waste
Site is unsafe for workers
Delays due to traffic management and lane closures
Design Risks | External Risks
Incomplete quantity estimates | Examples include a shifting regulatory environment, labor issues, changing customer priorities, government agency risks, and weather. Also to be considered are consultant and vendor contract risks, contract type and contractor responsibilities.
Insufficient design analysis
Complex hydraulic features
Surveys incomplete
Inaccurate assumptions during the planning phase
Environmental Risks | Organizational Risks
Unanticipated noise impacts | Examples include lack of prioritization of projects, inadequacy or interruption of funding, inexperienced and poorly developed and trained workforce, and resource conflicts with other projects in the organization.
Unforeseen Section 4(f) resources affected
Environmental clearance for borrow site required
Unanticiapated barriers to wildlife
Unforeseen air qulaity issues
External Risks | Project Management Risks
Project not fully funded | Examples include poor allocation of time and resources, inadequate quality of the project plan, lack of project manager delegated authority, and use of project management disciplines
Politically driven accelerated schedule
Permit agency actions cause unexpected delays
Public objections
Inflation and other market forces
Organizational Risks
Resource conflicts with other projects
Inexperienced staff assigned to project
Lack of specialized staff
Approval and decision processes cause delays
Priorities change on existing programs
Project Management Risks
Inadequate project scoping and scope creep
Consultant and contractor delays
Estimating and/or scheduling errors
Lack of coordination and communication
Unforeseen agreements required
Right of Way Risks
Unanicipated escalation in ROW values
Additional ROW may be needed
Acquisition of ROW may tke longer than anticipated
Discovery of hazardous waste during the ROW phase
Unforeseen railroad involvement

## Risk Ranking
Risk Ranking
These tables present examples of risk probability rankings, and risk impact rankings for the four project objectives - cost, time, scope and quality. They should be tailored to the individual project and the project stakeholders' risk thresholds. Risk impact rankings for opportunities can be developed in a similar manner.
Example 1
Risk Probability Ranking
Ranking | Probability
Very Low | Remote (10%)
Low | Unlikely (30%)
Medium | Likely (50%)
High | Highly Likely (70%)
Very High | Near Certainty (90%)
Risk Impact Ranking
Primary Objective
Ranking | Cost | Time | Scope | Quality
Very Low | No significant cost increase | Minimal schedule impact | Minimal scope change | Quality degradation barely noticeable
Low | <5% cost increase | <3 month delay | Changes in project limits or features with <5% cost increase | No deficiencies apparent
Medium | 5 - 7% cost increase | 3 - 6 month delay | Changes in project limits or features with 5 - 10% cost increase | Minimal deficiencies in constructability, operability, and safety
High | 7 -10% cost increase | 6 - 9 month delay | Major changes in project limits and features with >10% cost increase | Major deficiencies in the technical adequacy of the final product
Very High | >10% cost increase | >9 month delay | Scope does not meet original purpose and need | Final product not acceptable due to deficiencies
Example 2
Risk Probability Ranking
Ranking | Probability
Very Low | 1 - 9%
Low | 10 - 19%
Medium | 20 - 39%
High | 40 - 59%
Very High | 60 - 99%
Risk Impact Ranking
Primary Objective
Ranking | Cost | Time | Scope | Quality
Very Low | Insignificant cost increase | Insignificant time increase | Scope decrease barely noticeable | Quality degradation barely noticeable
Low | <10% cost increase | <5% time increase | Minor areas of scope affected | Only very demanding applications are affected
Medium | 10 - 20% cost increase | 5 - 10% time increase | Major area of scope affected | Quality reduction requires owner approval
High | 20 -40% cost increase | 10 - 20% time increase | Scope reduction unacceptable to owner | Quality reduction unacceptable to owner
Very High | >40% cost increase | >20% time increase | Project end item is effectively useless | Project end item is effectively useless

## Risk Matrix
Risk Matrix
The combination of the probability and impact rankings are visually displayed on a five-by-five probability and impact matrix. This method classifies a risk as either high (red), moderate (yellow), or low (green). The resulting three level risk classification can be adjusted for diferent projects and even for different risks within a project.
High Risk Events (Red) require priority action and aggressive response strategies. Specific action is warranted to reduce the probability of occurrence or the risk's negative impact.
Moderate Risk Events (Yellow) are either high probability low impact or low probability high impact events. The low probability high impact events are of more concern and require more oversight under this classification. They need to be monitored for changes.
Low Risk Events (Green) may not require proactive management action and can be eliminated from further assessment or periodically reassessed in the future until they are closed or occassionally elevated to a higher risk classification.

## Risk Response Strategies
Response Strategies
Strategies that deal with threats or risks that may have negative impacts on project objectives include:
Avoid Risk avoidance might be achieved by changing scope, adding time, or adding resources. Threats that arise early in the project can be avided by clarifying requirements, obtaining information, improving communication, or acquiring expertise.
Transfer Transfering risk requires shifting the negative impact of a threat, along with ownership of the response, to a third party. Risk transference nearly always involves payment of a risk premium to the party taking on the risk. Some examples of transference tools are insurance, performance bonds, warranties, guarantees, incentive/disincentive clauses, A+B contracts, fixed price or cost type contracts, etc.
Mitigate Risk mitigation implies a reduction in the probability and/or impact of an adverse event to an acceptable threshold. It may take resources and time and therfore represent a tradeoff of one objective for another, but it may still be preferable to going forward with an unmitigated risk. Monitoring the deliverables closely, increasing the number of parallel activities in the schedule, early involvement of regulatory agencies in the project, early and continuous outreach to communities/advocacy groups, impementing value engineering, performing corridor studies, adopting less complex processes, conducting more tests, or choosing a more stable supplier are examples of mitigation actions.
Acceptance The most common acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the risk. Otherwise, the risk is just accepted and addressed if and when it occurs.
Strategies that deal with opportunities or risks with potentially positive impacts on project objectives include:
Exploit This strategy hopes to eliminate the uncertainty associated with a particular upside risk by making the opportunity definitely happen.
Share Allocating ownership to a third party who is best able to capture the opportunity for the benefit of the project. Examples are joint ventures, partnerships, etc.
Enhance This strategy modifies the size of an opportunity by increasing probability and/or positive impacts, and by identifying and maximizing key drivers of these positive-impact risks.
Acceptance Either establishing a contingency reserve for a potential opportunity or just accepting the opportunity are two acceptance strategies.