## WFLHD471
CONTRACTOR QUALITY CONTROL PLAN WORKSHEET
Work Feature:
| Bid items associated with the work: | [6 empty] | WFLHD FORM 471
| Is a WFLHD 470 required for this feature of work? | Yes No | No
Add pages (attachments) as necessary.
|  | Contractor Quality Control Actions |  |  | PRODUCTION/POST-WORK
|  | Who will perform the task? | What will be done to accomplish the task? | When and where will activities be performed and at what frequency? | Date completed. |  | Purpose and Benefit
PREPARATORY QC ACTIVITY 1 | Independently and with contractor staff review contract rquirements plans and specifications. | [5 empty] | Assign QC individuals to be fully knowledgeable of the contract requirements. Use this individual to act as a resource for project staff to assist in determining requirements of the work. Knowledge of requirements will improve decision making for project staff allowing maximum performance and efficiency in completing work requirements.
PREPARATORY QC ACTIVITY 2 | Check and verify submittals, plans and materials certifications for contract requirements and submit to FHWA. Provide statement and signature of verification. | [5 empty] | Prompt and accurate review of submittal and certifications from fabricators and suppliers will ensure quick turnaround of FHWA acceptance. Repeated submittal transactions drains time and resources.
PREPARATORY QC ACTIVITY 3 | Check site conditions for constructability, including staging, disposal and storage areas. Identify potential quality control issues. Verify the materials delivered to the site conform to accepted materials certifications, submittals, plans and contract requirements. | [5 empty] | A visual review of site conditions that analyses constructability staging, materials deliverd and othe operational factors could uncover some aspects of the work that have not been forseen. Making a practice of this will increas productivity and ensure maximum efficiency during startup of operations.
PREPARATORY QC ACTIVITY 4 | Review construction staking to assure accuracy and sufficiency at each stage of construction.See Table 153-2 and Section 152 Construction Survey & Staking | [5 empty] | Completing a systematic check of construction staking to ensure sufficiency and accuracy can save costly delays and expensive rework because of inaccurate survey. Develop a cross check method to ensure that layout and staking is correct and appropriate for the work. Develop an understandings of the information that will be conveyed by the staking.
PREPARATORY QC ACTIVITY 5 | Complete operational work plan. Provide brief written narrative of the work activity describing methods, locations, crews, equipment and processes that will be used to complete the work. | [5 empty] | Developing a work plan ahead of time is key to efficient performance. Sharing that knowledge in written form is instrumental in obtaining cost efficient performance. Sudden changes in work plan and methods due to oversight of essential requirements can be fatal to cost efficiency.
START UP QC ACTIVITY 6 | Conduct pre-work meeting. Review contract requirements jointly with construction crew, foremen and FHWA personnel prior to beginning work. | [5 empty] | Keeping the crew and the FHWA staff informed of methods, special considerations and expectations developed in the operational workplan is critical to a successful operation. Good communication should lessen misunderstood job requirements, inefficiency and re-work.
PRODUCTION QC ACTIVITY 7 | Verify that the ongoing construction will result in the end product meeting the contract requirements. Verify by inspecting, measuring and testing. See table 153-1 & 153-2. Perform corrective actions |  |  |  |  | Final Report - As quality control activities (1) thru (9) are completed document dates completed and final descriptions of results or issues associated with the QC activities in the remaining columns. See 153.04(c) | The key to efficient production and acceptance is to ensure that adequate inspection and quality control has been performed prior to FHWA acceptance. Enabling your organization to perform quality control testing and inspection as the work is in the production stage allows adjustments to be made at an early stage. Rejection of completed work is costly and can be avoided by practicing good quality control. A structured approach to self-verification is beneficial.
PRODUCTION QC ACTIVITY 8 | Provide immediate presence to communicate status of work to FHWA personnel and contractor personnel for quality control issue resolution. | [5 empty] | Close and prompt contact with FHWA is beneficial to solving construction issues during early stages of work. The sooner that issues are resolved the more efficient and productive work can be. It is in both the contractors and the pwners interest to solve problems promptly as close to the issue as possible. Lengthy delays in finding the right personnel to resolve issues with cost time and wastes resources.
COMPLETION QC ACTIVITY 9 | Verify completed work meets contract requirements. Implement Notification of completion of Work as required. See 153.06 | [5 empty] | Self inspection of initial, production and followup work phases should be defined to ensure that work is meeting requirements as it is performed. This is an essential part of quality control to verify that the product meets contract requirements. It should include visual inspections, verification measurements and testing. When deficiencies are found, establish criteria for preventing recurrences.
| Contractor Quality Control Manager Approval Signature |  |  | QC Reports - As quality control activities (1) thru (9) are performed, provide reports of activities including discussions, reviews, inspections, measurements and testing results. Include deficiencies encountered and description of corrective actions completed. See 153.04(b)(1)
| _____________________________________________________ | DATE | ________________________
FHWA Acceptance Signature
| _____________________________________________________ | DATE | ________________________
*Grayed areas are not not required to be completed.
QC Reports - As quality control activities (1) thru (9) are performed, provide reports of activities including discussions, reviews, inspections, measurements and testing results. Include deficiencies encountered and description of corrective actions completed. See 153.04(b)(1)