## Sheet1
Contract Modification Tracking Report
Project Name
Project Number
Temporary Number | Description | PR Submitted | PR Approved | PR Amount | PR Amended | PR Amended Amount | IGE | Contractor's Price Proposal Requested | Contractor's Price Proposal Received | Pre Negotiation Memos | Price Negotiation Memos | SF30 Received | SF30A | WFLHD-10 | Database Report | CM Executed by Contractor | CM Executed by Government | Final Amount | Revised Fixed Completion Date | CM Number
A
B
C
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z
AA
BB
CC
DD
EE
FF
GG
HH
II
JJ
Example
Temporary Number | Description | PR Submitted | PR Approved | PR Amount | PR Amended | PR Amended Amount | IGE | Contractor's Price Proposal Requested | Contractor's Price Proposal Received | Pre Negotiation Memos | Price Negotiation Memos | SF30 Received | SF30A | WFLHD-10 | Database Report | CM Executed by Contractor | CM Executed by Government | Final Amount | Revised Fixed Completion Date | CM Number
A | Slide Area at MP 2.5 | 2015-05-01 | 2015-05-06 | 10000 | NA | NA | X | 2015-04-24 | 2015-04-30 | NA | 2015-04-24 | X | X | X | X | 2015-05-06 | 2015-05-08 | 9985 | 2016-08-16 | 0002
B | Adding a Pilot Car | 2015-05-01 | 2015-05-06 | 70000 | 2015-05-25 | 72000 | X | 2015-04-24 | 2015-04-30 | NA | 2015-05-01 | X | X | X | X | 2015-05-06 | 2015-05-08 | 72000 | NA | 0003
C | Erosion Control for Stockpiles | 2015-03-06 | 2015-03-07 | 5500 | NA | NA | X | 2015-02-28 | 2015-03-07 | NA | 2015-03-01 | X | X | X | X | 2015-03-15 | 2015-03-20 | 5494.5 | NA | 0001
D | Revises Ped Railing fastern | 2015-06-30 | 2015-07-07 | -3.5 | NA | NA | X | 2015-05-28 | 2015-06-15 | 2015-05-28 | 2015-06-10 | X | X | X | X | 2015-07-15 | 2015-07-20 | -3.5 | 2016-08-22 | 0004