## Title
Critical Path Method (CPM) for
PROJECT NUMBER
PROJECT NAME
xx% Submission
|  | Lead Designer: | NAME
|  | Project Manager: | NAME
Created for
Park/Refuge/Forest Name
2022-01-13
Created by
EFL-TM-HWY-05(12)
ITEM
NO PAY ITEM
xx% Submission
15% Submission
30% Submission
70% Submission
90% Submission
95% Submission
100% Submission
U.S. Department of Transportation
Federal Highway Administration
Eastern Federal Lands Highway Division
Quantum Park
22001 Loudoun County Parkway
Building E-2, Suite 200
Ashburn, Virginia 20147

## Roadway
Work Activity Production Rates for PROJECT NUMBER
| Critical Path | FP Sect. | Item | Unit | Base Rate | Plan Quantity | Adjustment Factors |  |  |  |  | Time Required | Remarks
[7 empty] | Location | Traffic | Complexity | Soil | Quantity |  |  |  | Adjusted Rate
0 |  | 103 | Design Duration | Days | 10 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
1 | Yes | 104 | Submittals & Review | Days | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 20 |  | 1 | 20
2 | Yes | 152 | De-mobilization | Days | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 4 |  | 1 | 4
3 | Yes | 152 | Mobilization | Days | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 5 |  | 1 | 5
0 |  | 152 | Compute and stake centerline | L.F. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
0 |  | 152 | Cross Sectioning and Slope Staking | Acres | 3 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3
4 | Yes | 157 | Silt Fence | L.F. | 2000 | 5000 | 1 | 1 | 1 | 1 | 1 | 3 |  | 1 | 2000
0 |  | 157 | Temporary Turf Establishment | Acres | 10 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 201 | Clearing & Grubbing (Optimal) | Acres | 2.6 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3
0 |  | 201 | Clearing & Grubbing (Rugged terrain) | Acres | 0.5 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1
0 |  | 203 | Demo. Of Buildings | Each | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1
0 |  | 203 | Removal of Asphalt Pavement | S.Y. | 1000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1000
0 |  | 203 | Removal of Curb & Gutter | L.F. | 600 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 600
0 |  | 203 | Removal of Sidewalk | L.F. | 400 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 400
0 |  | 203 | Removal of Guardrail | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 203 | Removal of Pipe Culvert | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 203 | Removal of Rigid Pavement | S.Y. | 1100 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1100
0 |  | 203 | Removal of Sign | Each | 6 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 6
0 |  | 203 | Sawcut Pavement (AC) | L.F. | 200 |  | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 200
0 |  | 203 | Sawcut Pavement (PCC) | L.F. | 800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 800
0 |  | 204 | Conserve Topsoil | C.Y. | 2500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2500
0 |  | 204 | Embankment | C.Y. | 2200 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2200
0 |  | 204 | Excavation, Channel | C.Y. | 650 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 650
0 |  | 204 | Excavation, Large quantity projects | C.Y. | 5000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 5000
0 |  | 204 | Excavation, Minor Drainage Structures | C.Y. | 250 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 250
5 | Yes | 204 | Excavation, Roadway | C.Y. | 600 | 2000 | 1 | 1 | 1 | 1 | 1 | 3 |  | 1 | 600
0 |  | 204 | Excavation, Small/Irregular Area Projects | C.Y. | 850 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 850
0 |  | 204 | Excavation, Trench | C.Y. | 800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 800
0 |  | 204 | Fine Grading | S.Y. | 2000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2000
0 |  | 204 | Granular Embankment, Special | C.Y. | 1120 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1120
0 |  | 205 | Rock Blasting | C.Y. | 1750 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1750
0 |  | 207 | Placing Earthwork Geotextile | S.Y. | 10000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10000
0 |  | 208 | Structure Excavation | C.Y. | 300 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 300
0 |  | 213 | Sub-grade Stabilization | S.Y. | 8000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 8000
0 |  | 213 | Sub-grade Stabilization with Asphalt | S.Y. | 3000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3000
0 |  | 213 | Sub-grade Stabilization with Cement | S.Y. | 1100 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1100
0 |  | 213 | Sub-grade Stabilization with Lime | S.Y. | 1800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1800
0 |  | 251 | Loose Riprap | Tons | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 251 | Riprap, Concrete | S.Y. | 170 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 170
0 |  | 255 | Barrier Walls, Slip Form | L.F. | 630 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 630
0 |  | 255 | Wall, MSE (max.) | S.F. | 1000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1000
0 |  | 255 | Wall, MSE (min.) | S.F. | 215 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 215
0 |  | 258 | Major Retaining Walls | S.F. | 210 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 210
0 |  | 258 | Retaining Walls, Cast in Place | L.F. | 5 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 5
0 |  | 301 | Aggregate Base | Tons | 1360 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1360
0 |  | 301 | Aggregate Base Small/Irregular Projects | Tons | 680 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 680
0 |  | 303 | Pulverizing, 8-inch Depth | S.Y. | 4700 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 4700
0 |  | 304 | Shoulder Reconditioning | L.F. | 8000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 8000
6 | Yes | 305 | Aggregate Topsoil Course | S.Y. | 10000 | 70000 | 1 | 1 | 1 | 1 | 1 | 7 |  | 1 | 10000
7 | Yes | 401 | Asphalt Surface | Tons | 1500 | 42000 | 1 | 1 | 1 | 1 | 1 | 28 |  | 1 | 1500
0 |  | 403 | Asphalt Base | Tons | 600 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 600
0 |  | 409 | Asphalt Surface Treatment | S.Y. | 4000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 4000
8 | Yes | 409 | Tack Coat (Add 1 Day to Broom) | Tons | 50 | 50 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 50
0 |  | 410 | Slurry Seal | S.Y. | 8000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 8000
0 |  | 411 | Prime Coat or Tack Coat | S.Y. | 8000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 8000
9 | Yes | 413 | Asphalt Pavement Milling (1.5") | S.Y. | 5000 | 62000 | 1 | 1 | 1 | 1 | 1 | 12 |  | 1 | 5000
0 |  | 413 | Asphalt Pavement Milling (4.5") | S.Y. | 6800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 6800
0 |  | 418 | Full Depth Reclamation Patch, Type I | S.Y. | 3500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3500
0 |  | 501 | Concrete Paving | S.Y. | 2500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2500
0 |  | 501 | Concrete Paving, Continuously Reinforced | S.F. | 2200 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2200
0 |  | 502 | Concrete Repair | S.Y. | 30 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 30
0 |  | 552 | Bridge Deck Repair | LPSM | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1
0 |  | 602 | Box Culverts, Class A Conc. | C.Y. | 20 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 20
0 |  | 602 | Box Culverts, Precast | L.F. | 40 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 40
0 |  | 602 | Drainage Conc. Pipe (24" to 54") | L.F. | 72 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 72
0 |  | 602 | Drainage Conc. Pipe (60 in. & greater) | L.F. | 48 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 48
0 |  | 602 | Drainage Conc. Pipe 18" | L.F. | 144 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 144
0 |  | 602 | Drainage Concrete Pipe 15" | L.F. | 168 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 168
0 |  | 602 | Drainage Corrug.Metal 18" | L.F. | 205 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 205
0 |  | 602 | Pipe Culverts 24-inch and Smaller | L.F. | 250 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 250
0 |  | 602 | Pipe Culverts 48-inch and Larger | L.F. | 50 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 50
0 |  | 602 | Pipe Culverts, 30-inch to 42-inch | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 602 | Storm Sewer 24-inch or Less | L.F. | 300 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 300
0 |  | 602 | Storm Sewer 30-inch or Greater | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 604 | Inlets, Adjust | Each | 5 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 5
0 |  | 604 | Inlets/Manholes/Concrete Headwalls | Each | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2
0 |  | 605 | Drainage Blanket | Tons | 1200 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1200
0 |  | 605 | Edge Drain | L.F. | 4000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 4000
0 |  | 605 | Underdrain | L.F. | 500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 500
0 |  | 608 | Paved Waterway | S.F. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
0 |  | 609 | Curb & Gutter (Hand Placed) | L.F. | 400 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 400
0 |  | 609 | Curb & Gutter (Machine Placed) | L.F. | 800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 800
0 |  | 609 | Curb& Gutter Radial (Hand Placed) | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 609 | Curb, Asphalt | L.F. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
0 |  | 609 | Curb, Concrete | L.F. | 1000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1000
0 |  | 609 | Curb, Stone | L.F. | 350 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 350
0 |  | 611 | Utility 12" Ductile Iron | L.F. | 105 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 105
0 |  | 611 | Utility 12" PVC | L.F. | 320 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 320
0 |  | 615 | Concrete Driveway | S.Y. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 615 | Concrete Entrance | S.Y. | 80 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 80
0 |  | 615 | Sidewalk | S.F. | 20 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 20
0 |  | 617 | Guardrail | L.F. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
0 |  | 617 | Guardrail Terminals | Each | 2 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 617 | Guardrail, Cable | L.F. | 850 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 850
0 |  | 617 | Guardrail, Timber | L.F. | 600 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 600
0 |  | 617 | Guardrail, W-beam or box beam | L.F. | 600 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 600
0 |  | 617 | Install Impact Attenuator | Each | 3 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 617 | Order Impact Attenuators | Days | 30 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 30
0 |  | 618 | Precast concrete barrier | L.F. | 800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 800
0 |  | 619 | Fencing | L.F. | 1000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1000
0 |  | 619 | Fencing, Chain Link | L.F. | 300 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 300
0 |  | 619 | Fencing, Wood Rail | L.F. | 150 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 150
0 |  | 619 | Fencing, Woven Wire | L.F. | 500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 500
0 |  | 620 | Stone Masonry Guardwall | L.F. | 50 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 50
0 |  | 624 | Placing Topsoil | S.Y. | 4000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 4000
0 |  | 625 | Seeding | Acres | 2.5 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
10 | Yes | 625 | Turf Establishment | Acres | 5 | 7 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 5
0 |  | 626 | Trees | Each | 22 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 22
0 |  | 627 | Sodding | S.Y. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
0 |  | 633 | Delineators | Each | 500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 500
0 |  | 633 | Erecting Overhead Signs | Days | 10 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 633 | Erecting Signs | S.F. | 1000 |  | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 1000
0 |  | 633 | Order Overhead Sign Struct. | Days | 80 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 80
0 |  | 633 | Order Sign Material | Days | 60 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 60
0 |  | 634 | Arrows/Letters | Each | 50 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 50
11 | Yes | 634 | Pavement Markings | L.F. | 15000 | 100000 | 1 | 1 | 1 | 1 | 1 | 7 |  | 1 | 15000
0 |  | 634 | Stop Bars, etc. | L.F. | 500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 500
0 |  | 634 | Temporary Tape Markings | L.F. | 1000 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1000
12 | Yes | 635 | Initial Traffic Control | LPSM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 10
0 |  | 635 | Temporary Concrete Barrier | L.F. | 800 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 800
0 |  | 635 | Temporary Detour | Days | 6 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 636 | Electrical Conduit | L.F. | 400 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 400
0 |  | 636 | Electrical Wire | L.F. | 3500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3500
0 |  | 636 | Erecting Lighting | Days/support | 3 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | 636 | Illuminaire Poles (Manufacture & Test) | Days | 120 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 120
0 |  | 636 | Lighting, Total Installation Lumin. | Each | 2 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 2
0 |  | 636 | Major Traffic Signals | Days/Intersec. | 40 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 40
0 |  | 636 | Minor Traffic Signals | Days/Intersec. | 15 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 15
0 |  | 636 | Ordering Lighting Material | Days | 60 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 60
0 |  | 636 | Ordering Signal Equip. | Days | 30 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 30
0 |  | 636 | Phasing Allowance | Days/Phase | 3 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 3
0 |  | 636 | Signal Poles (Manufacture & Testing) | Days | 120 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 120
0 |  | 646 | Mailbox | Each | 10 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 10
0 |  | Bridge | Construct Bridge | Days | 50 |  | 1 | 1 | 1 | 1 | 1 | 0 | Quantity from "Bridge" tab (critical path) | 0 | 50
[10 empty] | Critical Path = | 92 | Working Days
Assumptions/Notes:
A.) Production rates are units/day based on an 8 hr. day unless otherwise noted,
such as by Days or HOUR.
B.) Several of the adjustment factors should have similar impacts on production,
so generally it is recommended not to reduce the base quantity by more than 2 factors except
in special circumstances.
C.) Sensitivity Factors are estimated according to their effect on normal production.
If the scheduler disagrees with the factors for a specific application, he or she should
develop a unique value. For example, excavation rates could be widely variable.
If the average figure sounds off for your project, consider making additional calculations
based on the excavation equipment most likely to be used.
D.) Utility 12" and drainage pipes include excavation/backfill for good soil conditions in a 4-5 ft.+/-
trench. Additional time for excavation should be estimated by the scheduler
for unfavorable conditions.
E.) Consult with your Traffic Engineering Section for production rates for specialty
items to make sure you account for the necessary review and fabrication times.
Yes
| Demobil | Demobil | Mobilization | 0
| 1 | 1 | 1 | 1
| 0.4 | 0.4 | 0.6
| Location | Location | Traffic Conditions
| 1 | 1 | 1
| 0.85 | 0.85 | 0.88
| 0.75 | 0.75 | 0.7
| Complexity | Complexity | 1
| 1 | 1
| 0.85 | 0.85
| 0.7 | 0.7
| Soil Cond. | Soil Cond. | Quantity
| 1 | 1 | 1
| 0.85 | 0.85 | 0.88
| 0.65 | 0.65 | 0.75

## Start
Critical | No. | Items | Quantity | Rate | Time Req'd | Start on Day | Finish Day |  | Items | quantity | rate | time req'd | finish
Yes | 1 | Submittals & Review | 1 | 20 Days | 20 | 1 | 20 | Yes | Submittals & Review | 1 | 20 Days | 20 | 20
Yes | 3 | Mobilization | 1 | 5 Days | 5 | 21 | 25 | Yes | Mobilization | 1 | 5 Days | 5 | 25
Yes | 12 | Initial Traffic Control | 1 | 10 LPSM | 1 | 26 | 26 | Yes | Initial Traffic Control | 1 | 10 LPSM | 1 | 26
Yes | 4 | Silt Fence | 5000 | 2000 L.F. | 3 | 27 | 29 | Yes | Silt Fence | 5000 | 2000 L.F. | 3 | 29
Yes | 5 | Excavation, Roadway | 2000 | 600 C.Y. | 3 | 30 | 32 | Yes | Excavation, Roadway | 2000 | 600 C.Y. | 3 | 32
Yes | 9 | Asphalt Pavement Milling (1.5") | 62000 | 5000 S.Y. | 12 | 33 | 44 | Yes | Asphalt Pavement Milling (1.5") | 62000 | 5000 S.Y. | 12 | 44
Yes | 8 | Tack Coat (Add 1 Day to Broom) | 50 | 50 Tons | 1 | 45 | 45 | Yes | Tack Coat (Add 1 Day to Broom) | 50 | 50 Tons | 1 | 45
Yes | 7 | Asphalt Surface | 42000 | 1500 Tons | 28 | 46 | 73 | Yes | Asphalt Surface | 42000 | 1500 Tons | 28 | 73
Yes | 6 | Aggregate Topsoil Course | 70000 | 10000 S.Y. | 7 | 74 | 80 | Yes | Aggregate Topsoil Course | 70000 | 10000 S.Y. | 7 | 80
Yes | 11 | Pavement Markings | 100000 | 15000 L.F. | 7 | 81 | 87 | Yes | Pavement Markings | 100000 | 15000 L.F. | 7 | 87
Yes | 10 | Turf Establishment | 7 | 5 Acres | 1 | 88 | 88 | Yes | Turf Establishment | 7 | 5 Acres | 1 | 88
Yes | 2 | De-mobilization | 1 | 4 Days | 4 | 89 | 92 | Yes | De-mobilization | 1 |  | 4 | 92
| 13 | [5 empty] | 0 | [5 empty] | 0
| 14 | [5 empty] | 0 | [5 empty] | 0
| 15 | [5 empty] | 0 | [5 empty] | 0
| 16 | [5 empty] | 0 | [5 empty] | 0
| 17 | [5 empty] | 0 | [5 empty] | 0
| 18 | [5 empty] | 0 | [5 empty] | 0
| 19 | [5 empty] | 0 | [5 empty] | 0
| 20 | [5 empty] | 0 | [5 empty] | 0
| 21 | [5 empty] | 0 | [5 empty] | 0
| 22 | [5 empty] | 0 | [5 empty] | 0
| 23 | [5 empty] | 0 | [5 empty] | 0
| 24 | [5 empty] | 0 | [5 empty] | 0
| 25 | [5 empty] | 0 | [5 empty] | 0
| 26 | [5 empty] | 0 | [5 empty] | 0
| 27 | [5 empty] | 0 | [5 empty] | 0
| 28 | [5 empty] | 0 | [5 empty] | 0
| 29 | [5 empty] | 0 | [5 empty] | 0
| 30 | [5 empty] | 0 | [5 empty] | 0
| 31 | [5 empty] | 0 | [5 empty] | 0
| 32 | [5 empty] | 0 | [5 empty] | 0
| 33 | [5 empty] | 0 | [5 empty] | 0
| 34 | [5 empty] | 0 | [5 empty] | 0
| 35 | [5 empty] | 0 | [5 empty] | 0
| 36 | [5 empty] | 0 | [5 empty] | 0
| 37 | [5 empty] | 0 | [5 empty] | 0
| 38 | [5 empty] | 0 | [5 empty] | 0
| 39 | [5 empty] | 0 | [5 empty] | 0
| 40 | [5 empty] | 0 | [5 empty] | 0
| 41 | [5 empty] | 0 | [5 empty] | 0
| 42 | [5 empty] | 0 | [5 empty] | 0
| 43 | [5 empty] | 0 | [5 empty] | 0
| 44 | [5 empty] | 0 | [5 empty] | 0
| 45 | [5 empty] | 0 | [5 empty] | 0
| 46 | [5 empty] | 0 | [5 empty] | 0
| 47 | [5 empty] | 0 | [5 empty] | 0
| 48 | [5 empty] | 0 | [5 empty] | 0
| 49 | [5 empty] | 0 | [5 empty] | 0
| 50 | [5 empty] | 0 | [5 empty] | 0

## CPM
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 |  | 1
| Choose option for BEST display | [5 empty] | Choose color option | [125 empty] | 2 | 1
| 2 | [131 empty] | 3
| Each block in chart equals 2 day(s) | [130 empty] | 2 | 4
| PROJECT NUMBER - xx% CPM - SCHEDULE A | [131 empty] | 5
7.5
|  | WORK DAYS | [129 empty] | Grayscale | 10
[10 empty] | 10 | [9 empty] | 20 | [9 empty] | 30 | [9 empty] | 40 | [9 empty] | 50 | [9 empty] | 60 | [9 empty] | 70 | [9 empty] | 80 | [9 empty] | 90 | [9 empty] | 100 | [9 empty] | 110 | [9 empty] | 120 | [8 empty] | 130 |  |  | Color 1 | 15
Yes | Submittals & Review | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [110 empty] | Color 2 | 20
Yes | Mobilization | [20 empty] | 1 | 1 | 1 | 1 | 1
Yes | Initial Traffic Control | [25 empty] | 1
Yes | Silt Fence | [26 empty] | 1 | 1 | 1
Yes | Excavation, Roadway | [29 empty] | 1 | 1 | 1
Yes | Asphalt Pavement Milling (1.5") | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Yes | Tack Coat (Add 1 Day to Broom) | [44 empty] | 1
Yes | Asphalt Surface | [45 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Yes | Aggregate Topsoil Course | [73 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Yes | Pavement Markings | [80 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Yes | Turf Establishment | [87 empty] | 1
Yes | De-mobilization | [88 empty] | 1 | 1 | 1 | 1
Index
[8 empty] | Critical Path | [14 empty] | Non-critical Path | [76 empty] | Project duration = 92 working days
Assumptions
| Item | Quantity | [5 empty] | Rate | [5 empty] | Days | [17 empty] | Item | [25 empty] | Quantity | [5 empty] | Rate | [5 empty] | Days | [19 empty] | Item | [25 empty] | Quantity | [5 empty] | Rate | [5 empty] | Days
| Submittals & Review | 1 | [5 empty] | 20 Days | [5 empty] | 20
| Mobilization | 1 | [5 empty] | 5 Days | [5 empty] | 5
| Initial Traffic Control | 1 | [5 empty] | 10 LPSM | [5 empty] | 1
| Silt Fence | 5000 | [5 empty] | 2000 L.F. | [5 empty] | 3
| Excavation, Roadway | 2000 | [5 empty] | 600 C.Y. | [5 empty] | 3
| Asphalt Pavement Milling (1.5") | 62000 | [5 empty] | 5000 S.Y. | [5 empty] | 12
| Tack Coat (Add 1 Day to Broom) | 50 | [5 empty] | 50 Tons | [5 empty] | 1
| Asphalt Surface | 42000 | [5 empty] | 1500 Tons | [5 empty] | 28
| Aggregate Topsoil Course | 70000 | [5 empty] | 10000 S.Y. | [5 empty] | 7
| Pavement Markings | 100000 | [5 empty] | 15000 L.F. | [5 empty] | 7
| Turf Establishment | 7 | [5 empty] | 5 Acres | [5 empty] | 1
| De-mobilization | 1 | [5 empty] | 4 Days | [5 empty] | 4

## Bridge (hidden)
Work Activity Production Rates for PROJECT NUMBER
| Critical Path | FP-03 Sect. | Item | Unit | Base Rate | Plan Quantity | Adjustment Factors |  |  |  |  | Time Required | Remarks
[7 empty] | Location | Traffic | Complexity | Soil | Quantity |  |  |  | Adjusted Rate
0 |  | 152 | Compute and stake centerline | L.F. | 1500 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1500
101 | Yes | 152 | Cross Sectioning and Slope Staking | Acres | 3 | 5 | 1 | 1 | 1 | 1 | 1 | 2 |  | 1 | 3
0 |  | 157 | Sediment Traps | C.Y. | 400 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 400
0 |  | 203 | Demo. Of Buildings | Each | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1
102 |  | 203 | Removal of Asphalt Pavement | S.Y. | 1500 | 5000 | 1 | 1 | 1 | 1 | 1 | 3 |  | 1 | 1500
0 |  | 301 | Aggregate Base | Tons | 1360 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1360
0 |  | 615 | Sidewalk | S.F. | 1550 |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 1550
103 | Yes | 635 | Construct Bridge | Days | 120 | 1 | 1 | 1 | 1 | 1 | 1 | 120 | Lump sum item with adjustment factors | 1 | 120
0 |  | 636 | Minor Traffic Signals | Days/Intersection | 15 |  | 1 | 1 | 1 | 1 | 1 | 0 | Days per special unit of measure | 0 | 15
0 |  | 636 | Ordering Signal Equip. | Days | 30 |  | 1 | 1 | 1 | 1 | 1 | 0 | Lump sum item, no adjustment factors | 0 | 30
[10 empty] | Critical Path = | 122 | Working Days
Assumptions/Notes:
A.) Production rates are units/day based on an 8 hr. day unless otherwise noted,
such as by Days or POUR.
B.) Several of the adjustment factors should have similar impacts on production,
so generally it is recommended not to reduce the base quantity by more than 2 factors except
in special circumstances.
C.) Sensitivity Factors are estimated according to their effect on normal production.
If the scheduler disagrees with the factors for a specific application, he or she should
develop a unique value. For example, excavation rates could be widely variable.
If the average figure sounds off for your project, consider making additional calculations
based on the excavation equipment most likely to be used.
Yes
| Demobil | Demobil | Mobilization | 0
| 1 | 1 | 1 | 1
| 0.4 | 0.4 | 0.6
| Location | Location | Traffic Conditions
| 1 | 1 | 1
| 0.85 | 0.85 | 0.88
| 0.75 | 0.75 | 0.7
| Complexity | Complexity | 1
| 1 | 1
| 0.85 | 0.85
| 0.7 | 0.7
| Soil Cond. | Soil Cond. | Quantity
| 1 | 1 | 1
| 0.85 | 0.85 | 0.88
| 0.65 | 0.65 | 0.75

## Bridge Start (hidden)
Critical | No. | Items | Quantity | Rate | Time Req'd | Start on Day | Finish Day
Yes | 101 | Cross Sectioning and Slope Staking | 5 | 3 Acres | 2 | 1 | 2
0 | 102 | Removal of Asphalt Pavement | 5000 | 1500 S.Y. | 3 | 3 | 5
Yes | 103 | Construct Bridge | 1 | 120 Days | 120 | 6 | 125
| 104 | [5 empty] | 0
| 105 | [5 empty] | 0
| 106 | [5 empty] | 0
107
108
109
110
111
| 112 | [5 empty] | 0
| 113 | [5 empty] | 0
| 114 | [5 empty] | 0
| 115 | [5 empty] | 0
| 116 | [5 empty] | 0
| 117 | [5 empty] | 0
| 118 | [5 empty] | 0
| 119 | [5 empty] | 0
| 120 | [5 empty] | 0
| 121 | [5 empty] | 0
| 122 | [5 empty] | 0
| 123 | [5 empty] | 0
| 124 | [5 empty] | 0
| 125 | [5 empty] | 0
| 126 | [5 empty] | 0
| 127 | [5 empty] | 0
| 128 | [5 empty] | 0
| 129 | [5 empty] | 0
| 130 | [5 empty] | 0
| 131 | [5 empty] | 0
| 132 | [5 empty] | 0
| 133 | [5 empty] | 0
| 134 | [5 empty] | 0
| 135 | [5 empty] | 0
| 136 | [5 empty] | 0
| 137 | [5 empty] | 0
| 138 | [5 empty] | 0
| 139 | [5 empty] | 0
| 140 | [5 empty] | 0
| 141 | [5 empty] | 0
| 142 | [5 empty] | 0
| 143 | [5 empty] | 0
| 144 | [5 empty] | 0
| 145 | [5 empty] | 0
| 146 | [5 empty] | 0
| 147 | [5 empty] | 0
| 148 | [5 empty] | 0
| 149 | [5 empty] | 0
| 150 | [5 empty] | 0
| 151 | [5 empty] | 0

## Bridge CPM (hidden)
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 |  | 1
| Choose option for BEST display | [5 empty] | Choose color option | [125 empty] | 2 | 1
[132 empty] | 2 | 3
| Each block in chart equals 2 day(s) | [130 empty] | 2 | 4
| PROJECT NUMBER - xx% BRIDGE CPM | [131 empty] | 5
|  | WORK DAYS | [129 empty] | Grayscale
[10 empty] | 10 | [9 empty] | 20 | [9 empty] | 30 | [9 empty] | 40 | [9 empty] | 50 | [9 empty] | 60 | [9 empty] | 70 | [9 empty] | 80 | [9 empty] | 90 | [9 empty] | 100 | [9 empty] | 110 | [9 empty] | 120 | [8 empty] | 130 |  |  | Color 1
Yes | Cross Sectioning and Slope Staking | 1 | 1 | [128 empty] | Color 2
0 | Removal of Asphalt Pavement |  |  | 1 | 1 | 1
Yes | Construct Bridge | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Index
[8 empty] | Critical Path | [14 empty] | Non-critical Path | [76 empty] | Project duration = 122 working days
Assumptions
| Item | Quantity | [5 empty] | Rate | [5 empty] | Days | [17 empty] | Item | [25 empty] | Quantity | [5 empty] | Rate | [5 empty] | Days | [19 empty] | Item | [25 empty] | Quantity | [5 empty] | Rate | [5 empty] | Days
| Cross Sectioning and Slope Staking | 5 | [5 empty] | 3 Acres | [5 empty] | 2
| Removal of Asphalt Pavement | 5000 | [5 empty] | 1500 S.Y. | [5 empty] | 3
| Construct Bridge | 1 | [5 empty] | 120 Days | [5 empty] | 120
1
2
3
4
5

## Bridge_VDOT (hidden)
Work Activity Base Production Rates
Item | Unit | Base Rate
MOT Setup
Impact Attenuators | EA | 2
Median Barrier - Install | LF | 800
Removing Exst. Guardrail | LF | 1500
Shoulder Improvements | LF | 500
Signs, Install Small (Sheet) | EA | 30
Temporary Detour Bridge - Install | Days | 13
Traffic Control Setup | Days | 2
Excavation/Demolition
Cofferdam | Days | 15
Dismantle/Remove Exst. Concrete Deck | SY | 275
Dismantle/Remove Exst. Structure | SY | 50 | Example Production Rate Calculation for Bridge Footing:
Minor Excavation | CY | 250 | Conditions: Rural Bridge Replacement, Traffic Detoured, Small Two Lane structure
Sheet Piling - Drive | SF | 500 | Calculation: 20 C.Y. x 1.0 x .75 = 15 C.Y.
Structure Excavation | CY | 300
CBR30 Backfill/Compact Abutment | TON | 100
Substructure Items
Drilled Shafts | EA | 0.3
Epoxy Injection Crack Repair | LF | 80
Reinforcing Steel | TON | 2.5
Retaining Walls (CIP) | SF | 400
Riprap - Dumped | TON | 700
Riprap - Grouted | TON | 50
Riprap - Machine Placed | TON | 250
Slope Protection - Concrete | SY | 750
Steel Piles - Prebored | LF | 250
Steel Piles - Driven | LF | 400
Concrete Piles - 8" to 14" | LF | 300
Concrete Piles - 24" to 30" | LF | 325
Substructure Footings - Form and Place | CY | 20
Substructure Neatwork - Form and Place | CY | 10
Substructure Footing - Place Seal | CY | 15
Superstructure Items
Approach Slabs | DAY | 5
Beam Repairs - Concrete Beam End | EA | 0.25
Beam Repairs (Steel) - Bolted | EA | 0.5
Beam Repairs (Steel) - Welded | EA | 1
Bridge Deck - Form & Place Reinf. Steel | SY | 50
Bridge Deck - Overlay | SY | 500
Bridge Deck - Pour New | SY | 850
Bridge Deck Grooving | SY | 550
Bridge Deck - Sidewalk/Raised Median | LF | 80
CIP Conc. Slab Span - Install Falsework | SF | 250
CIP Conc. Slab Span - Pour | CY | 10
Concrete Diaphragms - Form & Pour | CY | 11
Concrete Removal - Sub/Super Patch | SY | 15
Concrete Removal - Type B Patch | SY | 50
Concrete Removal - Type C Patch | SY | 10
Concrete Surface Color Coating | SY | 100
Expansion Dam | EA | 4
Expansion Joint Reconstruction | LF | 25
Expansion Joint Removal | LF | 250
Expansion Joint Sealer | LF | 450
Milling (Concrete - per 1/2" depth) | SY | 1600
Parapet - Hand Formed | LF | 50
Parapet - Slip Formed | LF | 200
Metal Rail Parapet | LF | 100
Kansas Corrall Parapet | LF | 20
Pedestrian Fence | LF | 7
Prestressed Conc. Beam Erection | LF | 400
Shotcrete | SY | 65
Struct. Steel Surface Prep. (Method 1) | SF | 3000
Struct. Steel Surface Prep. (Method 2) | SF | 240
Struct. Steel Surface Prep. (Method 3) | SF | 600
Struct. Steel Surface Prep. (Method 4) | SF | 200
Struct. Steel Surface Prep. (Method 5) | SF | 1100
Struct. Steel Surface Prep. (Method 6) | SF | 6000
Struct. Steel Surface Prep. (Method 7) | SF | 7500
Structural Steel - Painting (per coat) | SF | 2000
Structural Steel Erection | TON | 10
Structural Steel Erection | LF | 200
Timber Bridge Deck | SF | 200
Finishing Items/MOT Teardown
CIP Conc. Slab Span - Remove Falsework | SF | 500
Median Barrier - Remove | LF | 800
Sheet Piling - Pull | SF | 500
Temporary Detour Bridge - Remove | Days | 4
Traffic Control Teardown | Days | 2
Concrete Curing |  | Cure days/Pour
Deck overlays - Assume 20 CY of material placement per day
LMC | POUR | 5
HESLMC | POUR | 3
VESLMC | POUR | 1
New Construction
Substructure Footings | POUR | 2
Substructure Neatwork | POUR | 5
Bridge Deck Concrete | POUR | 7
Parapet | POUR | 7
Component Level Production Rates |  |  | (Recommended for use at Field Inspection before all quantity details are known)
Item | Unit | #Days | Special Notes:
Abutments | Days | 8 | Add 1 day for each 400' of piles. Add time for cofferdam/structure exc. Includes normal curing conditions.
Piers or Bents | Days | 15 | Add 1 day for each 400' of piles. Add time for cofferdam/structure exc. Includes normal curing conditions.
Concrete Deck Span 20'-40' | Days | 15 | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 41'-60' | Days | 21 | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 61'-80' | Days | 27 | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 81'-100' | Days | 33 | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 101'-120' | Days | 39 | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 121'-140' | Days | 45 | Includes form, rebar, pour, normal cure time.
Steel Beams (Plate Girder) | Each |  | Add 2-3 days/span for diaphragms
Steel Beams (Rolled Steel) | Each |  | Add 1 day/span for diaphragms
Concrete Beams | Each |  | Add 2-3 days/span for diaphragms
New Bridge Construction | L.F.
1 station (100 ft.) of 12 ft. lane roadway rural or new construction | Days | 2 | Includes clearing & grubbing, grading, pavement structure, guardrail, seeding, and light drainage work.
1 station (100 ft.) of 12 ft. lane roadway urban or widening work | Days | 4 | Includes above plus curb & Gutter, Drainage, Utilities, and items commonly encountered in urban work.
Note: Component Level Production Rates are recommended for estimating time at the field inspection or early planning stages before quantities are known.

## Hidden(2) (hidden)
No. | Critical | Items | Quantity | Rate | Time Req'd
1 | Yes | Submittals & Review | 1 | 20 Days | 20
2 | Yes | De-mobilization | 1 | 4 Days | 4
3 | Yes | Mobilization | 1 | 5 Days | 5
4 | Yes | Silt Fence | 5000 | 2000 L.F. | 3
5 | Yes | Excavation, Roadway | 2000 | 600 C.Y. | 3
6 | Yes | Aggregate Topsoil Course | 70000 | 10000 S.Y. | 7
7 | Yes | Asphalt Surface | 42000 | 1500 Tons | 28
8 | Yes | Tack Coat (Add 1 Day to Broom) | 50 | 50 Tons | 1
9 | Yes | Asphalt Pavement Milling (1.5") | 62000 | 5000 S.Y. | 12
10 | Yes | Turf Establishment | 7 | 5 Acres | 1
11 | Yes | Pavement Markings | 100000 | 15000 L.F. | 7
12 | Yes | Initial Traffic Control | 1 | 10 LPSM | 1
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
101 | Yes | Cross Sectioning and Slope Staking | 5 | 3 Acres | 2
102 | 0 | Removal of Asphalt Pavement | 5000 | 1500 S.Y. | 3
103 | Yes | Construct Bridge | 1 | 120 Days | 120
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151