# RISK AND OPPORTUNITY MANAGEMENT PLAN

| Project Name: |  |
| --- | --- |
| Project Manager: |  |

| ### 1. Instructions for Using this Document |  |
| --- | --- |
| Section I | Risk Assessment Questionnaire |
| - Use Section I of this template to identify risks and opportunities that will impact the project and the level of threat or benefit they pose to the project’s success. In this section, characteristics are grouped in typical categories of project risk and opportunity. High, medium and low risk or opportunity ratings are assigned to descriptions of each project characteristic. This list of potential risks and opportunities is not exhaustive and is intended to provide a starting point only. - The completed questionnaire and checklist will identify the project’s risk and opportunity factors. The results from the completed questionnaire and checklist should be used as guidelines; there may be other factors that will lower or raise the risk level. Having many high-risk characteristics does not necessarily mean the project will fail. However, it does mean that a plan must be put into place to address each potential high-risk factor. |  |
| - Section II | - Typical High-Risk Problems/Response Actions – |
| - Use Section II of this template to analyze identified risks and opportunities and plan appropriate responses. Early warning signs and examples of problems that may result from certain types of high risks are listed alongside examples of activities that may be undertaken to mitigate or respond to each risk. - For each high-risk factor identified in Section I, create a response plan in the Risk Response Plan document to ensure that the risk is mitigated and does not impact project success. Consider the example activities in Section II as examples of potential responses. The project team may suggest additional response actions. After creating response plans for all the high-risk factors, look at the medium-level risks to determine whether the impact is severe enough to warrant an entry into the Risk Response Plan as well. If so, create entries in the Risk Response Plan for the medium-risk factors. Low-risk factors may be considered assumptions, that is, there is a potential for problems, but because the risk is low, you are “assuming” that the condition will not occur. The Risk Response Plan is used throughout the project to monitor and control risks. |  |

|  |  |  |  |  |  |  |  |  | - Section I |  |  | - Risk and Opportunity Identification and Assessment Questionnaire |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | - Characteristics |  |  | - Low Impact | - Medium Impact | - High Impact |
| - ORGANIZATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A. Project Scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | - A1 |  |  |  | - The scope of the project is: |  | - [ ] Well-defined and understood | - [ ] Somewhat defined, but subject to change | - [ ] Poorly defined and/or likely to change |
|  |  |  |  |  |  |  | - A2 |  |  |  | - All Cooperating Agencies are: |  | - [ ] identified and Committed | - [ ] Identified and not committed | - [ } Unknown |
|  |  |  |  |  |  |  | - A3. |  |  |  | - Historical information is (e.g. as-builts, traffic/accident data): |  | - [ ] Available |  | - [ ]Not available |
|  |  |  |  |  |  |  | - A4. |  |  |  | - Environmental Constraints: |  | - [ ] Categorical Exclusion | - [ ] Environmental Assessment | - [ ] Environmental Impact Statement |
| - B. Project Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | - B1. |  |  | - Are the project’s major milestones: |  | - [ ] Flexible - may be established by the project team | - [ ] Firm - pre-established | - [ ] Fixed - pre-established by a specific commitment or legal requirement and beyond the team’s control |
|  |  |  |  |  |  |  |  | - B2. |  |  | - The total estimated effort hours are: |  | - [ ] Less than 2,000 | - [ ] Between 2,000 and 5,000 | - [ ] Greater than 5,000 |
|  |  |  |  |  |  |  |  | - B3. |  |  | - Project duration (design) is estimated at: |  | - [ ] Less than 2 years | - [ ]2 to 4 years | - [ ] Greater than 4 years |
| - C. Project Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | - C1. |  |  |  | - The project budget (Preliminary Engineering) is based upon: |  | - [ ] CFLHD Work Breakdown Structure Spreadsheet |  | - [ ] Other methods or techinques |
|  |  |  |  |  |  |  | - C2. |  |  |  | - The Preliminary Construction Cost Estimate is based upon: |  | - [ ] CFLHD Risk Based Spreadsheet |  | - [ ] Other methods or techniques |
|  |  |  |  |  |  |  | - C3. |  |  |  | - Program amount matches or exceeds the estimated cost and is stable. |  | - [ ] Funding is greater than estimated construction cost and/or is expected to be stable. | - [ ] Funding meets estimated construction cost and expected to remain relatively stable. | - [ ] Funding is less than estimated construction cost and/or its stability is highly uncertain. |
| - D. Management/Senior Leadership Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - D1. |  |  |  |  | - The project sponsor (FLMA, State, County) is: |  | - [ ] Identified and committed | - [ ] Identified | - [ ] Not identified or not commited |
| - E. Project Human Resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - E1. |  |  |  |  |  | - The Project Manager’s experience and training is: |  | - [ ] Recent success in managing projects similar to this one | - [ ] Recent success in managing a project not similar to this one or trained and no actual experience | - [ ] No recent experience or project management training |
|  |  |  |  |  | - E2. |  |  |  |  |  | - Describe the experience of cross functional team personnel with the tools and techniques to be used. |  | - [ ] Experienced in use of tools and techniques | - [ ] Formal training in use of tools and techniques but little or no practical experience | - [ ] No formal training or practical experience in use of tools and techniques |
|  |  |  |  |  | - E3. |  |  |  |  |  | - The cross functional team is: |  | - [ ] Located together |  | - [ ] Dispersed at multiple sites |
| - F. Other Business or Organizational Impacts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - F1 |  |  |  |  |  |  | - CFLHD processes, procedures, policies require: |  | - [ ] Little or no change | - [ ] Occasional to frequent changes | - [ ] Substantial change |
|  |  |  |  | - F3. |  |  |  |  |  |  | - The number of functional areas the project will affect are: |  | - [ ] 1-4 | - [ ] 4-6 | - [ ] 6 or more |
| - GENERAL – Technical and Performance Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - G. Technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - G1. |  |  |  |  |  |  |  | - The technology being utilized consists of: |  | - [ ] Mature (existing design software, hardware, languages, databases, and tools) | - [ ] Emerging | - [ ] Leading Edge (new design software, hardware, languages, databases, or tools (or new releases)) |
|  |  |  | - G2. |  |  |  |  |  |  |  | - The technical requirements for this project are: |  | - [ ] Similar to others in CFLHD |  | - [ ] New and complex |
| - PROJECT MANAGEMENT - Planning, Issue and Change Management, Quality Assurance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - I. Evaluation of PM Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - I1. |  |  |  |  |  |  |  |  | - The overall assessment of Project Management risk |  | - [ ] The project is well planned and will be carried out in a manner consistent with the CFLHD project management guidelines |  | - [ ] Planning for this project is inconsistent, incomplete or in other ways of poor quality AND/OR there are problems with project process that must be addressed |
| - EXTERNAL – Vendor, Legal, Environmental, Regulatory, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - J.A/E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - J1. |  |  |  |  |  |  |  |  |  | - If project is outsourced: |  | - [ ] A/E is familiar in this market |  | - [ ] A/E is new to this market |
|  | - J2. |  |  |  |  |  |  |  |  |  | - Are A/E firms required and committed to the project? |  | - [ ] No – A/E firms are not required | - [ ] Yes – Some A/E firms are required (less than 50%) and are expected to be signed before start of project | - [ ] Yes – Project will be staffed by A/E and/or contractors’ commitment is not expected to be complete prior to start of project |

| - Section II |  | - Typical High-Risk Problems/Response Actions |  |
| --- | --- | --- | --- |
|  | - High-Risk Factors/Potential Problems |  | - Risk Response Actions |
| - A. Scope |  |  |  |
| - A1. | - The scope of the project is poorly defined: - Hard to provide sound estimates - May spend time and cost on areas out of scope - Hard to gather concise requirement - Difficult to write project definition and work plan - Hard to invoke scope-change procedures - Project deliverables are poorly defined |  | - Focus on firming up scope in the planning process - Define various components of scope, such as what departments are affected, what deliverables are expected, what type of information is required - Clearly define what is out of scope for the project - Begin to define business requirements at a high level and then work upward to define scope - Ask project sponsor to make decision on conflicting scope statements - Document all scope assumptions when providing estimates of work, cost, or duration - Use pictures or diagrams to communicate scope and options - Establish firm scope-change procedures up front - Ensure the project definition and business requirements are formally approved and signed off on - Distribute scope statements to all stakeholders for confirmation - Do not begin project until scope is clear |
| - A2. | - The stakeholders are unknown: - Not knowing the stakeholders early in the project phase will impact the scope of the project - A new stakeholder that was not identified earlier who have a potential negative influence in the project |  | - Allocate more time to identify all potential stakeholders early in the process - Conduct public meetings if necessary very early in the planning process to identify all stakeholders - Get the public involved. |
| - A3. | - Historical information is not available: - Will require work and resources to create data (traffic data, pavement analysis, accident data) - Hard to estimate scope and cost |  | - Try to contact the Agency/County to find information - Conduct traffic counts early in the process to assess traffic trends and forecast future demands - Conduct public meeting to gather historical data, accidents, maintenance areas. - Get seed funds to conduct traffic studies early in the process |
| - A4. | - Environmental constraints: - If a project requires an EIS, the risk is very high due to the environmental analysis and mitigation measures. |  | - Consider other project alternatives - Consider reducing the scope of work - Try to get buy-in from all the stakeholders early in the process on the preferred alternative - If internal environmental staff is not experienced, get the A/E environmental firm involved early in the process. |
| - B. | - Schedule |  |  |
| - B1. | - The project’s major milestones and operational dates are fixed. They were pre-established externally or by legal requirements beyond control of the project team: - Work must be scheduled to fit within this schedule constraint - Most likely the schedule requirements will be impossible to meet - Hurried activity and schedule requirements will cause errors - Will create conflicts |  | - Re-negotiate schedule requirements to fit required activities - Re-negotiate scope to limit activities deemed doable in allotted time - Establish new agreements with client agencies/costumers - Put aggressive project tracking and monitoring plan in place - Communicate status reports on regular basis |
| - B2. | - High number of estimated effort hours: - Implication of a high number of effort hours is that there are many people involved and more complexity - Harder to communicate effectively with the team - Bottlenecks can occur when decisions are needed quickly - More chance of people problems - Increased chance of turnover - More people to train |  | - Use a project management tool to control resource utilization - Have team members utilize weekly status reports to report on progress against their assigned work plan activities - Organize team-building activities to build cohesion - Schedule status meetings to keep people informed of project status - Utilize structured internal procedures for scope, issue, quality, and risk management - Break the project into smaller, shorter tasks - Reduce available project work time per person, per day to recognize additional people and team-related activities |
| - B3. | - Long estimated project duration: - Harder to manage the schedule - Easier for the team and the customer to drift or lose focus - More chance that project will lose organizational commitment - More chance business requirements will change - More chance of change in software or hardware versions - Difficult to instill sense of urgency at the beginning of project - More chance of team and customer turnover |  | - Break the project into smaller, shorter subprojects - Identify clear milestones to check that the project is on schedule - Be diligent using formal change management procedures - Rotate team members into different roles to keep up the interest level - Strive to get ahead of schedule as early as possible. - Instill a sense of urgency from the start of the project - Organize team-building activities to build cohesion and reduce friction |
| - C. | - Budget |  |  |
| - C1. | - Project budget was not established with any proven tool or by any experienced person: - Budget will most likely not be accurate - Budget will not be structured in manor to facilitate tracking and control. - There will be unrealistic expectations for what can be accomplished within the budget. |  | - Re-estimate the project using proven tools and experienced personnel - Revise scope to fit within the funding available - Don’t start the project until a better budget can be established |
| - C2. | - Project funding is less than the estimated cost and is unstable: - Project will be unable to fulfill expectations - Project will likely exceed it’s funding |  | - Renegotiate scope to fit within the funding available - Don’t start the project until an adequate budget or lesser scope is established |
| - D. | - Management/Senior Leadership Support |  |  |
| - D1. | - The project sponsor is not identified or not enthusiastic: - Project may not get the resources it needs - Project may not have the long-term commitment needed - Political battles may delay the project - Issues and change requests may not be resolved in a timely manner |  | - Establish a strong steering committee to help guide the project - Establish a process for resolving disputes between departments - Try to identify a different sponsor - Ask the sponsor to delegate full authority to another person who can act on their behalf - Don’t start the project |
| - E. | - Human Resources |  |  |
| - E1. | - Project management experience is light: - May take longer to define the project and build work plan - May make more mistakes in judgment, causing rework and project delays - More difficulty organizing and managing a complex project - May not be familiar with sound project management practices - May not know when to call for help |  | - Provide up-front project management training - Designate a more senior person to coach and mentor the project manager - Break the project into smaller pieces that are easier to manage - Put a strong quality-assurance process in place to ensure the project is on the right track - Make sure the major deliverables are formally approved - Utilize strong team leaders and team members to bring additional experience to bear |
| - E2. | - Project management processes are unfamiliar or will not be used: - Team may have a difficult time understanding how to raise issues, scope changes, and risks - Project may get out of control as the internal processes become more complex and harder to manage - Communication will tend to be poorer - Project deliverables might be completed in different formats - Issues may not be addressed in a timely manner, scope changes may be adopted without thought of impact to the project, risks may be ignored, and quality may be compromised - Chance that the project may be in trouble before it is recognized |  | - Provide training to the project manager and project team on sound project management processes and procedures utilizing both the internal and external processes for delivering projects at CFLHD - Assign an experienced project management coach or mentor to the project - Break the project into smaller pieces that can be managed with less-rigorous project management - Define and gain approval for a set of project management procedures before the project starts, including issues management, change management, risk management, and quality management - Create a solid communication plan to ensure everyone knows what’s going on and can provide feedback - Solicit input on issues, risk, scope change, and quality concerns on an ongoing basis |
| - E3. | - Project team is located in dispersed locations: - Harder to communicate effectively - Less team interaction and cohesion - Harder to build personal relationship with the entire team - Some members may feel isolated and not a part of the team - Technology problems may result in productivity decrease |  | - Try to get the team into one location, at least for the length of the project - Create an aggressive communication plan to ensure the team communicates effectively - Hold regular meetings where the entire team meets face-to-face - Schedule team-building activities where the entire team meets face-to-face - Have backup methods to communicate if the primary technology fails - Maintain frequent contact by phone with remote team members - Create a central repository to hold the project documentation that all team members can access |
| - F. | - Business or Organizational Impacts |  |  |
| - F1. | - CFLHD processes and policies require substantial change: - Policy changes could delay the project - People will be confused with new processes, which will affect their ability to utilize the solution - Possibility that new processes will not be fully integrated at first - Possible void if new processes don’t fully cover all contingencies - System functions may not be used if not supported by correct procedures - Substantial change in processes may result in destructive behavior - People may fear loss of jobs in a new organization |  | - Document all current policies and processes and ensure that they are correct - Communicate precisely how the new processes differ from the old ones - Communicate potential changes as far in advance as possible - Ensure the customers are defining the process and policy changes - Have one person responsible for all process and policy changes - Create an aggressive communication plan to keep customers engaged and informed - Use the new processes in a pilot project first to ensure they are workable and correct - Include the successful implementation of new policies and processes as part of the performance criteria for managers - Be open to customer input on process changes—for better ideas and to allow them to feel they have impact |
| - F2. | - High number of functional disciplines are affected: - Coordination is more complex - Approvals can be more cumbersome and lengthy - More difficult to reach consensus - More people and groups to involve in planning and requirements - Harder to know the major stakeholders of the various departments - Implementation is harder and more complex |  | - Establish a formal approval process - Create a steering committee to represent the entire stakeholder community - Keep the sponsor engaged and ready to intervene in the various departments - Include representative from each organization in requirements, quality assurance, and testing - Include opportunities for people from the various departments to meet and interact - Work with the team on strict adherence to overall project objectives and priorities - Use consensus-building techniques when at all possible |
| - G. | - Technology |  |  |
| - G1. | - The project technology is new and unfamiliar (or new releases): - Learning curve may result in lower initial productivity - May be integration problems between old and new technology - Resistance to technology changes may cause the project to be delayed - May be difficulty testing the new technology - Technology may not be installed or configured correctly, which will lead to project delays - New tools can lead to longer delivery times - New technology may require substantial conversion efforts - System performance may be poor while expertise is gained in optimizing and configuring the technology |  | - Provide as much training on the new technology as practical, as early as possible - Train everyone who needs to install, use, or support the new technology - Make arrangements to rely on vendor technical specialists, when needed - Use outside consultants who are familiar with the technology - Make sure there is an adequate test environment where the technology can be utilized without affecting production - Ensure that solid analysis is completed regarding the new technology functions, features, and capabilities - Create procedures and standards for how the new technology should be utilized - Create a pilot test or prototype to utilize the new technology in a small way at first |
| - G2. | - The technical requirements are new and complex: - May be difficult to understand the requirements and the implications of design decisions - May be integration issues between old and new technology - May be difficulty testing the complex technology - The more complex the technology, the greater the risk that problems will occur - Problems with incompatible technologies may not be uncovered until integration or system testing |  | - Utilize system and technical design documents to clearly lay out how the technology fits together - Define the overall system technical architecture and have it approved by knowledgeable people in your company - Create a pilot project to utilize the new technology in a small way at first - Try to substitute more proven and familiar technology in the architecture |
| - H. | - Performance |  |  |
| - H1. | - Performance objectives are unclear or unstated or unrealistic (e.g. everything will be perfect) - The project team may be bogged down trying to meet minor performance objectives while the major ones are slipping away - The team may be subject to imposition of new performance requirements during the project if they are not written down at the start - This could be a no-win project since it is not possible to meet unrealistic objectives |  | - Make sure that all performance objectives are in writing, agreed to by the project team and approved by the Sponsor - Insist that any change in expectations regarding performance objectives be issued as a formal Change Request |
| - I. | - Project Management |  |  |
| - I1. | - Planning for this project is inconsistent, incomplete or in other ways of poor quality AND/OR there are problems with project process that must be addressed: - Work on the project may be uncoordinated and unproductive - The project may be subject to Scope Creep - With poor or absent project plans it is unlikely that the project will meet performance objectives |  | - Follow the Organization’s Project Management Methodology - Complete the recommended project templates and obtain approval from key stakeholders - Address and correct any identified project process issues - Follow and update the project plans throughout project execution |
| - J. | - A/E Firm |  |  |
| - J1. | - A/E firm is new to this market: - Possibility that A/E firm may not survive and leave you with no support - Learning curve might delay start of project - No prior relationships from which to build a quick partnership - Unfamiliar with CFLHD processes |  | - Train A/E staff early in the process - Make sure the A/E is a part of the project team early in the process - Maintain an A/E log to track problems with the deliverables - Establish agreements with the A/E firm stipulating support level and problem resolution times |